## Slide 1
Midterm Progress Report
Karthik Mylavarapu
kmylavarapu3
GT id : 903754308
Soccer Analytics Capstone — Trilemma Foundation Georgia Tech MSA Spring 2026 Practicum

## Slide 2
Project Overview
Goal: Build an open-source analytics pipeline that ingests public match event data and produces interactive player/team analytics dashboards.
Data Sources:
  StatsBomb: 3,464 matches, 12.2M events across major European leagues (La Liga, Premier League, Serie A, Ligue 1, Bundesliga) and international competitions
  Polymarket: 8,549 betting markets with $3B+ total trading volume, 1.1M individual trades spanning April 2025 — January 2026
Key Challenge: IDs are NOT normalized across datasets — StatsBomb team IDs do not map to Polymarket market slugs. Entity resolution is a critical early task.
Track Selected: Track 2 — Soccer Analytics Dashboard

## Slide 3
Work Completed: Infrastructure & Data Pipeline
Repository Setup
  Forked official template repo, installed all dependencies
  Downloaded and organized both StatsBomb and Polymarket datasets
  Verified data integrity with starter EDA template
Custom Analytics Modules (3 Python modules, ~1,400 LOC)
  entity_resolution.py — Fuzzy team name matching between StatsBomb and Polymarket (150+ teams mapped)
  feature_engineering.py — Possession chain builder, xG flow, PPDA, Field Tilt, Expected Threat (xT), team style classifier
  market_analysis.py — Market efficiency metrics, volume analysis, odds volatility, competition breakdown
Enhanced Dashboard
  Extended template with Top Players by xG and Most Active Players charts
  Updated footer and branding for 2026

## Slide 4
Work Completed: EDA Key Findings
StatsBomb Event Analysis
  Pass completion rate: 77.7% overall — uniform across competitions
  88,023 shots with xG data; mean xG per shot = 0.10
  Average 2.85 goals per match; La Liga shows highest scoring
  Messi leads with 363.4 cumulative xG from 2,670 shots
Polymarket Market Analysis
  Champions League Winner markets: >$1B volume (33% of total)
  Trading peaks during European evening hours (17:00–22:00 UTC)
  Buy/Sell ratio: 82% BUY vs 18% SELL — strong bullish sentiment
  Only 38% of markets have any trade activity

## Slide 5
Work Completed: Predictive Modeling Baseline
Research Question: Does event-level shot quality predict match outcomes?
Model: OLS regression — goal_diff ~ xg_diff
  goal_diff = home_score − away_score
  xg_diff = home_xG − away_xG
Results (3,457 matches):
  Slope = 1.055 — each unit of xG advantage translates to ~1 goal advantage
  R² = 0.475 — xG differential explains 47.5% of variance in actual goal differential
  Intercept ≈ 0.045 — minimal home advantage effect in xG-adjusted model
Interpretation: A single feature derived entirely from event data explains nearly half of outcome variance. This validates xG-based features as a foundation for dashboard analytics.

## Slide 6
Work Completed: Advanced Metrics Pipeline
Possession Chains — sequence of events by same team until turnover
  Segments matches into possession sequences with chain-level summaries
PPDA (Passes Per Defensive Action) — measures pressing intensity
  Lower PPDA = more intense pressing (High < 10, Medium 10–15, Low > 15)
Field Tilt — territorial dominance via final-third passing share
  Percentage of total final-third passes belonging to each team
Expected Threat (xT) — positional value using 12×8 grid
  Pre-computed threat values increase toward opponent's goal
Team Style Classifier — categorizes teams as Possession-based, High-pressing, Counter-attacking, or Balanced
  Based on pass completion, chain length, and high recovery percentage

## Slide 7
Work Completed: Entity Resolution
Challenge: StatsBomb and Polymarket use different team identifiers
  e.g., "Arsenal FC" (StatsBomb) vs "arsenal" (Polymarket slug)
Approach:
  Name normalization — remove common suffixes (FC, CF, SC), normalize punctuation
  Team extraction from Polymarket questions — regex pattern matching
  Fuzzy matching — token overlap (Jaccard similarity) with configurable threshold
  Manual overrides for known mappings (15 major clubs)
Results:
  308 unique StatsBomb teams identified
  1,863 unique Polymarket team mentions extracted
  1,699 fuzzy match mappings generated
  Coverage: major European clubs well-covered; smaller/non-European clubs limited

## Slide 8
Plan: Remaining Work
1. Dashboard Development (Primary Deliverable)
  Interactive Dash application with xG flow visualization for individual matches
  Team style comparison views (radar charts, scatter plots)
  Player performance analytics (heatmaps, pass networks, xG leaders)
  Competition-level tactical metrics explorer (PPDA, Field Tilt across seasons)
2. Multi-Feature Predictive Modeling
  Extend baseline OLS model with PPDA, field tilt, pressure events, carry distance
  Forward feature selection to identify most informative event metrics
  Test temporal stability — do coefficients hold across seasons/competitions?
3. Market Comparison Analysis (Optional/Stretch)
  For matches with Polymarket coverage, compare model-implied probabilities vs. market odds
  Identify potential market inefficiencies around key events (goals, red cards)

## Slide 9
Timeline & Milestones
Completed (Weeks 1–6)
  Data pipeline setup and validation
  Entity resolution module
  Feature engineering pipeline (PPDA, xG flow, Field Tilt, xT, team styles)
  Market analysis module
  EDA deliverables (Executive + Technical notebooks)
  Baseline predictive model (R² = 0.475)
In Progress (Weeks 7–10)
  Interactive dashboard — core views and filtering
  Multi-feature modeling and evaluation
  Documentation and README updates
Planned (Weeks 11–14)
  Dashboard polish — responsive design, deployment
  Market comparison analysis (if time permits)
  Final report and presentation

## Slide 10
Questions?
Repository: github.com/kmylavarapu3/soccer-analytics-capstone-template